\

DEPLOYMENT  PLAN

|  | Day | Date | Group | Activity |
| --- | --- | --- | --- | --- |
| Week 1 | 1 | 22nd June | Announcing our Presence and Our Purpos | Setup and training of teachers |
|  | 2 | 23rd June | Setting Up |  |
|  | 3 | 24th June | Setting Up |  |
|  | 4 | 25 th June | Trainer of Trainers |  |
|  | 5 | 26 th June | Trainer of Trainers |  |
|  | 6 | 27 th June | SUPPORT |  |
|  | 7 | 28 th June |  |  |
| School 1 |
| Week 2 | 1 | 29 th June | Grades 1 & 2 | General concept of computing relevant to the grade and level of study |
|  | 2 | 30 th June | SUPPORT |  |
|  | 3 | 1st July | Grades 3 & 4 |  |
|  | 4 | 2nd July | SUPPORT |  |
|  | 5 | 3rd July | Grades 5 & 6 |  |
|  | 6 | 4th July | SUPPORT |  |
|  | 7 | 5 th July |  |  |
| Week 3 | 1 | 7 th July | Grades 1 & 2 | About the XO,s and Usage |
|  | 2 | 8 th July | SUPPORT |  |
|  | 3 | 9 th July | Grades 3 & 4 |  |
|  | 4 | 10 th July | SUPPORT |  |
|  | 5 | 11 th July | Grades 5 & 6 |  |
|  | 6 | 12 th July | SUPPORT |  |
|  | 7 | 13 th July |  |  |
| Week 4 | 1 | 14 th July | Grades 1 & 2 | Practical and Application Specific e.g. art, logic, arithmetic, games |
|  | 2 | 15 th July | SUPPORT |  |
|  | 3 | 16 th July | Grades 3 & 4 |  |
|  | 4 | 17 th July | SUPPORT |  |
|  | 5 | 18 th July | Grades 5 & 6 |  |
|  | 6 | 19 th July | SUPPORT |  |
|  | 7 | 20 th July |  |  |
| Week 5 | 1 | 21 th July | Grades 1 & 2 | Practical and Project for the students |
|  | 2 | 22 th July | SUPPORT |  |
|  | 3 | 23 th July | Grades 3 & 4 |  |
|  | 4 | 24 th July | SUPPORT |  |
|  | 5 | 25 th July | Grades 5 & 6 |  |
|  | 6 | 26 th July | SUPPORT |  |
|  | 7 | 27 th July |  |  |
| School 2 |
| Week 6 | 1 | 28 th July | Grades 1 & 2 | General concept of computing relevant to the grade and level of study |
|  | 2 | 29 th July | SUPPORT |  |
|  | 3 | 30 th July | Grades 3 & 4 |  |
|  | 4 | 31 th July | SUPPORT |  |
|  | 5 | 1st August | Grades 5 & 6 |  |
|  | 6 | 2nd August | SUPPORT |  |
|  | 7 | 3rdAugust |  |  |
| Week 7 | 1 | 4th August | Grades 1 & 2 | About the XO,s and Usage |
|  | 2 | 5 th August | SUPPORT |  |
|  | 3 | 6 th August | Grades 3 & 4 |  |
|  | 4 | 7 th August | SUPPORT |  |
|  | 5 | 8 th August | Grades 5 & 6 |  |
|  | 6 | 9 th August | SUPPORT |  |
|  | 7 | 10 th August |  |  |
| Week 8 | 1 | 11 th August | Grades 1 & 2 | Practical and Application Specific e.g. art, logic, arithmetic, games |
|  | 2 | 12 th August | SUPPORT |  |
|  | 3 | 13 th August | Grades 3 & 4 |  |
|  | 4 | 14 th August | SUPPORT |  |
|  | 5 | 15 th August | Grades 5 & 6 |  |
|  | 6 | 16 th August | SUPPORT |  |
|  | 7 | 17 th August |  |  |
| Week 9 | 1 | 18 th August | Grades 1 & 2 | Practical and Project for the students |
|  | 2 | 19 th August | SUPPORT |  |
|  | 3 | 20 th August | Grades 3 & 4 |  |
|  | 4 | 21 th August | SUPPORT |  |
|  | 5 | 22 th August | Grades 5 & 6 |  |
|  | 6 | 23 th August | SUPPORT |  |
|  | 7 | 24 th August |  |  |
| Week 10 | 1 | 25 th August |  | Meeting with local partners on the sustainability of the OLPC project |
|  | 2 | 26 th August |  |  |
|  | 3 | 27 th August |  |  |
|  | 4 | 28 th August |  |  |
|  | 5 | 29 th August |  |  |
|  | 6 | 30 th August |  |  |
|  | 7 | 31 th August |  |  |

PROJECT

As agents of change, the wards will be allow to train one person from the community who did not benefit from the training. During the project, other people from the community who did not benefit but are interested will be invited by the beneficiaries and trained by these beneficiaries on how to use the XOs and how to use the applications on XOs under our supervision. We also intended to create a web site for more information for dissemination.