Project Initiation Document

Introduction of XO laptops for (visual impaired) school students in Pskov and Nizhny Novgorod, Russia

Version 1.14

February 28. 2008

Harrie Vollaard

Contents

Chapter 1 Document history	3

Document history:	3

Distribution list:	3

Chapter 2 Introduction and background	4

Chapter 3 Project objectives	5

Chapter 4 Assumptions and constraints	5

Chapter 5 Project deliverables	5

Chapter 6 Description of work	5

Tasks and timelines (February 2008 – October 2008)	5

Success criteria	6

Risk management	6

Chapter 7 Project organization	6

Project members	7

Chapter 8 Project budget	7

# Document history

## Document history:

| Version | Date | Author |
| --- | --- | --- |
| Version 0.6 | February 9. 2008 | Harrie Vollaard |
| Version 0.9 | February 15. 2008 | Comments of Olga Ursova, Boris Yarmakhov, Gertie Clabbers |
| Version 0.91 | February 17. 2008 |  |

## Distribution list:

| Version | Date | Author |
| --- | --- | --- |
| Version 0.6 | February 9. 2008 | OLPC Russia, Foundation |
| Version 0.9 | February 15. 2008 | OLPC Russia, City Administration, Centre of Distance Learning, Nizhny Novgorod Pedagogical University |
| Version 0.91 | February 17. 2008 | OLPC The Netherlands, OLPC Global, OLPC Russia, City Administration Pskov, Centre of Distance Learning, Nizhny Novgorod Pedagogical University |

# Introduction and background

The mission of the One Laptop per Child association is to develop a low-cost laptop—the "$100 Laptop"—to revolutionize the way the children of the world are educated. The goal is to provide children around the world with new opportunities to explore, experiment, and express themselves (http://wiki.laptop.org/go/The_OLPC_Wiki). The laptop (XO) is a very cheap and sustainable device especially developed to work wherever in the world. Today several projects around the world are being deployed. Also Russia is one of the countries that have expressed an interest at the Ministry of Education level or higher. The grass root organization OLPC Russia is almost done with the localization of the XO software. There will be an opportunity to introduce the XO in Russia during the trip of Harrie Vollaard and Gertie Clabbers through Russia because the Foundation Meters Maken voor Millennium (Making Miles for Millennium) is able to finance the needed XO’s. The trip is focused on how to develop and stimulate OLPC-initiatives. They are doing that by generating publicity and raising funds.

The city Pskov (Russia) has a town twinning with Nijmegen (The Netherlands) which makes it easier to introduce the first XO’s, because there are already relationships with all the involved parties. The partnering organization in Pskov is The Center for Distance Learning Education (contact person - Olga Ursova). The city Nizhny Novgorod (Russia) is the other city to introduce the XO’s at a school for visual impaired children and at an ecological summer camp. The partnering organization in Nizhny Novgorod is the Nizhny Novgorod State University (contact person - Boris Yarmakhov). At the moment OLPC Russia volunteers community consists of 10 people - educators, translators, software developers, students. The reasons why a summer camp was chosen as a first event to introduce OLPC into Russian educational practice are the following:

- The summer camp environment provides plenty of opportunities for children to benefit such outstanding features of OLPC as connectivity, ruggedness and sun light friendly display viewing mode. While on field trips children will be using mesh network and reading from the laptop screen in the sun light.

- While on field trips children will create and share collections of digital objects (flora and fauna samples) and write about their experience in a collective diary/blog.

- Application of Scratch - a multimedia programming language recently optimized for XO will be tested as an environment for extracurricular activities.

- Children and teachers involved in the summer school activities will not feel any stress connected with the requirements of the school program which will allow to implement the model of ubiquitous computing at its best.

This is the best way to determine the added value of the XO in a field experiment.

The unique selling points of the projects are:

- First introduction of XO’s in Russia

- The special way of introduction generates publicity more easy

- Accessibility of the XO for visual impaired children

# Project objectives

The main objective of the project is to determine if One Laptop Per Child initiative can be successfully introduced in Russia. To achieve this objective two pilot initiatives need to be done:

- Introduction in Pskov

Introduction of 10 XO’x in Pskov at different schools and to the different stakeholders within Pskov.

- Introduction in Nizhny Novgorod

  - Introduction of 20 XO’s at the Nizhny Novgorod Pedagogical University to the Nizhny Novgorod educators (schools also for visual impaired children and colleges). June, 6-10 (TBA) together with

  - Introduction of the XO to students at an ecological summer camp in Nizhny Novgorod.

# Assumptions and constraints

- Localization of the XO is not a part of the project. It is a continuing process but will be on a sufficient level at the time of introduction.

# Project deliverables

- 10 localized XO’s in Pskov for The Center for Distance Learning Education and City Administration Pskov (funds by Foundation, localization by OLPC Russia)

- 20 localized XO’s at the school for visual impaired children and at an ecological camp Nizhny Novgorod (funds by Foundation, localization by OLPC Russia)

- Text2Speech software for visual impaired children

- IT infrastructure in Nizhny Novgorod (funds by Foundation, localization by OLPC Russia)

- Stakeholder analysis; The analysis gives the insight what the success criteria will be to introduce XO’s at a larger scale in Pskov and Russia (OLPC Russia).

- Report of the visits for publicity purposes (Foundation Meters Maken voor Millennium)

- Evaluation report Nizhny Novgorod on the added value of the XO for students (OLPC Russia)

- Evaluation report Pskov with a go/no go for larger scale deployment (OLPC Russia)

# Description of work

## Tasks and timelines (February 2008 – October 2008)

- Generate funds for the introduction of the XO’s in Pskov and Nizhny Novgorod, Foundation, OLPC Russia

- Achieve commitment from local government Nijmegen and Stichting Stedenband Nijmegen – Pskov for the project, Foundation

- Achieve commitment from local government Pskov for the project, The Center for Distance Learning Education

- XO application and distribution, Foundation and OLPC Russia

- Text2Speech software development, OLPC, Foundation

- Generate publicity in The Netherlands, Foundation

- Generate publicity in Russia, OLPC Russia

- Determine schools, OLPC Russia, City Administration Pskov and The Center for Distance Learning Education

- Determine how to introduce the sample XO laptops at the schools and teachers, City Administration Pskov and The Center for Distance Learning Education

- Determine agenda for stay at Pskov, May 22. – May 25.

    - Meeting with stakeholders (OLPC Russia, IT, Foreign Department, City Administration) in Pskov, May 22.

    - Orientation in Pskov on educational level with the person in charge for education, May 23.

    - School visits and introduction of some sample XO laptops on different schools,  May 23. – May 24.

- Generate publicity local and internationally about the visit, Foundation

- Presentation in Nizhny Novgorod, June 6 -10., OLPC Russia, Nizhny Novgorod Pedagogical University

- Summer camp at Nizhny Novgorod, July, OLPC Russia, Nizhny Novgorod Pedagogical University

## Gantt Chart

## Success criteria

- Commitment of all stakeholders in Pskov; evaluation report

- Added value of the XO for student at the school for visual impaired children and the ecological camp;

- Test of the usability of Text2Speech software for visual impaired children.

- 15 summer camp students will learn how to use XO laptop/ mesh network.

- A collection of Nizhny Novgorod flora and fauna digital objects will be created.

- A repository of XO based Scratch scripts will be built.

- Teachers and students participating in the summer camp will reflect on their experience in a collective blog.

## Risk management

- Cooperation of government and schools (The Center for Distance Learning Education, Foundation)

- XO delivered on time (OLPC Russia, Foundation)

- XO delivered in Russia (OLPC Russia)

# Project organization

## Project members

- OLPC Russia (Boris Yarmakhov, Olga Ursova, Evgeny Patarakin)

- Center of Distance Learning Education Pskov

- Nizhny Novgorod Pedagogical University

- City Administration Pskov (Tatjana Rumjantseva)

- Foundation Meters Maken voor Millennium; Making Miles for Millennium (Harrie Vollaard, Gertie Clabbers)

- Schools

  - Lya van den Hoogen, primary school Klein Heyendaal, Nijmegen

  - School 21, Pskov (connection with Dutch school)

  - Palkinskaya school and Seredkinskaya school

- IT company Pskov (Nikolaj Timofeev)

# Project budget

| Activities | Costs (EURO) | Costs (Rubles) |
| --- | --- | --- |
| Project management 400 hr | 0 | 0 |
| Hardware costs |  |  |
| 30 XO Pskov and Nizhny Novgorod |  |  |
| IT Infrastructure |  |  |
| USB GPRS Modem Novatel Ovation MC950D Router Billion BiPAC 7300GX 3G/ADSL2 3 x Notepower Solar Laptop Computer Charger USB GPS Navigator GLOBALSAT BU353 SIRFSTAR III USB GPS RECEIVER Nova 5000 portable digital laboratory LEGO® MINDSTORMS® NXT set |  |  |
| Software |  |  |
| Development software application for Visual Impaired Children | pm | pm |
| Travel costs related to XO-project |  |  |
| Transport costs of XO |  |  |
| Promotional costs |  |  |
| Total |  |  |

Appendix

Involved OLPC members:

- Boris Yarmakhov (OLPC Russia. Nizhny Novgorod) is an educator with 15 years of experience of teaching at secondary school and University levels. Experienced user of PC systems and peripherals, digital photography, sound recording. Software skills include the Internet applications, distance learning systems, educational software.

- Yevgeny Patarakin (Scratch Russia) is an IT and education expert with 20+ years of experience. Proficient with Scratch, Logo, Moodle, wiki-wiki systems. Experienced user of PC systems and peripherals, GPS navigation.

- Olga Ursova (CDE, Pskov)  is an educational specialist in the area of distance learning systems. Experienced with PC systems, office applications, and various educational software.

- Harrie Vollaard (OLPC The Netherlands, Foundation Making Miles for Millennium) is innovation director with 10 years experience with new technology (biometrics, RFID, NFC, RIA, widgets, video communication, accessibility tools, Linux, GRID technology, iTV, virtual worlds etc.) in a major bank in the Netherlands. Capabilities: Innovation management and project management.

- Gertie Clabbers (OLPC The Netherlands, Foundation Making Miles for Millennium) is occupational therapist. She set up activities with people with a psychiatric background and support and stimulates them. Experience with PC and office applications.

# Text boxes

Nizhny Novgorod

Pskov